## BNPL functional
Epic/Story/Task | % | Optimistic | Best guess | Pessimistic | Standard Deviation | Triangular Distribution | Three-point estimation | Delivery Range
Initial Skeleton creation |  | 2 | 3 | 4
Infrastructure preperation |  | 4 | 5 | 6
User Management (Integration) |  | 5 | 10 | 15
Merchant Module: "Merchant Dashboard" section, summarized |  | 1 | 2 | 3
Merchant Module: "Merchant Orders section", List of Orders via several columns |  | 3 | 4 | 5
Merchant Module : "MerchantOrders section", Search option with some of the filters |  | 2 | 3 | 4
Merchant Module : "Merchant Orders section", Export functionality |  | 4 | 5 | 6
Merchant Module : "Merchant Orders section", Applications Refund (draw by Corzoid flow)
Merchant Module : "Merchant Applications", New Application Functionality (draw by Corzoid flow)
Merchant Module : "Merchant Applications", Creditworthiness checking (consider Integration) |  | 5 | 10 | 15
Merchant Module : "Merchant Applications", Receiving information via email |  | 3 | 4 | 5
Merchant Module : "Merchant Applications", Receiving information via web nothifications |  | 2 | 3 | 4
Merchant Module : "Merchant Applications", Receiving information via sms |  | 2 | 3 | 4
Merchant Module : "Merchant Administrative section", Information section for merchant |  | 2 | 3 | 4
Merchant Module : "Merchant Administrative section", Security section |  | 2 | 3 | 4
Merchant Module : "Merchant Administrative section", Password reset |  | 2 | 3 | 4
Merchant Module : "Merchant Administrative section", Notification Settings |  | 3 | 4 | 5
Merchant Module : "Merchant refund feature", cancel applications (draw by Corzoid flow)
User Module: "User Dashboard": Current (Available) Limit |  | 1 | 2 | 3
User Module: "User Dashboard": Upcoming Payments |  | 2 | 3 | 4
User Module: "User Dashboard": Transactions' history section with filtering |  | 3 | 4 | 5
User Module: "Payment Method's section": View attached cards |  | 3 | 4 | 5
User Module: "Payment Method's section": Add a new card |  | 1 | 2 | 3
User Module: "Payment Method's section": Remove attached card |  | 1 | 2 | 3
User Module: "User Applications", New Application Functionality (draw by Corzoid flow)
User Module: "User Applications", Receiving an invitation link and Temp. pass for a new deal |  | 1 | 2 | 3
User Module: "User Applications", Data finalization and approval for final approval (draw by Corzoid flow)
User Module: "User Applications", Terms and conditions page before finalization of the application |  | 1 | 2 | 3
User Module: "User Applications", Card attachment process during the financing flow (integration) |  | 5 | 10 | 15
User Module: "User Applications", Delivery of the agreements to the user via e-mail, after approving the application |  | 1 | 2 | 3
Admin Panel: "Fee management section", "Fee per transaction" |  | 1 | 2 | 2
Admin Panel: "Fee management section", "Fee based on the deal amount" |  | 1 | 2 | 2
Admin Panel: "Fee management section", "Cancelation fee" |  | 1 | 2 | 2
Admin Panel: "Fee management section", "Overdue fee" |  | 1 | 2 | 2
Admin Panel: "Merchant management", List of Merchants |  | 2 | 3 | 4
Admin Panel: "Merchant management", Create New Merchants |  | 2 | 3 | 4
Admin Panel: "Merchant management", Create Branches for Merchants |  | 1 | 2 | 3
Admin Panel: "Merchant management", Create Desks for Merchant's branches |  | 1 | 2 | 3
Admin Panel: "Merchant management", Manage (block, deactivate, etc) merchants |  | 1 | 2 | 3
Admin Panel: "Agreement management section", New financing agreement (draw by Corzoid flow)
Admin Panel: "Agreement management section", Overdue Template |  | 1 | 2 | 3
Admin Panel: "Merchant Orders section", List of Orders via several columns |  | 2 | 3 | 4
Admin Panel: "MerchantOrders section", Search option with some of the filters |  | 2 | 3 | 4
Admin Panel: "Merchant Orders section", Export functionality |  | 2 | 3 | 4
Admin Panel: "Merchant Orders section", Applications Refund |  | 1 | 2 | 3
Admin Panel: "Admin Dashboard" section, summarized |  | 1 | 1 | 1
Integration with FI |  | 5 | 10 | 15
Core estimation |  | 86 | 142 | 194 |  | 0 | 0 | 0 | 0
Load persentage (for Agile) % | 20 | 103.2 | 170.4 | 232.8 |  | 0 | 0 | 0 | 0
Management Risk % | 20 | 123.84 | 204.48 | 279.36 |  | 0 | 0 | 0 | 0
Total | [6 empty] | 0 | 0 | 0
Develpers | 3 | [5 empty] | 0 | 0 | 0

## User Managment
Epic/Story/Task | % | Optimistic | Best guess | Pessimistic | Standard Deviation | Triangular Distribution | Three-point estimation | Delivery Range
Merchant Module: "User Management" section, Create Branch
Merchant Module: "User Management" section, Create Desk
Merchant Module: "User Management" section, List of users (employees) with search
Merchant Module: "User Management" section, Filtering for the list of users
Merchant Module: "User Management" section, Reset Passwords for employees
Merchant Module: "User Management" section, Assign users to branches
Merchant Module: "User Management" section, Assign users to desks
User Module: "User Management": Login with temp pass
User Module: "User Management": Login with a permanent (standard) pass
User Module: "User Management": Forgot password
User Module: "User Management": Blocking for a wrong pass
User Module: "User Management", profile
User Module: "User Management", Password and Security
User Module: "User Management", Support
Core estimation |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Load persentage (for Agile) % | 20 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Management Risk % | 20 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total | [6 empty] | 0 | 0 | 0
Develpers | 3 | [5 empty] | 0 | 0 | 0

## BNPL user stories
ID | Title | Parent Name | Parent
371 | As an admin user I want to have New Financing agreement template in admin portal so that I can create an agreement to send to the users when financing | Agreement management | 346
372 | As an admin user, I want to have a Repayment template in admin portal, so that I can create an agreement to send to the users when making a repayment | Agreement management | 346
373 | As an admin user, I want to have Closure Template in admin portal, so that I can create an agreement to send to the users when closing the debts | Agreement management | 346
374 | As an admin user, I want to have Overdue Template in admin portal, so that I can create an agreement to send to the users when they will miss the scheduled payments | Agreement management | 346
375 | As an admin user, I want to have fixed fee per request, so that I can charge merchants when requesting for new financing | Fee management | 344
376 | As an admin user, I want to have fixed fee per transaction, so that I can charge merchants when financing users | Fee management | 344
377 | As an admin user, I want to have amount based fee, so that I can charge merchants when providing new financing | Fee management | 344
378 | As an admin user, I want to have Cancelation fee, so that I can charge users when canceling the deal | Fee management | 344
379 | As an admin user, I want to have Subscription fee, so that I can periodically charge users for using the service | Fee management | 344
380 | As an admin user, I want to have Overdue fee, so that I can charge the users who will not pay in time. | Fee management | 344
381 | As an admin user, I want to create new merchants, so that they can start using the product | Merchant management | 345
382 | As an admin user, I want to open new branches for Merchants, so that they can user the product in different locations | Merchant management | 345
383 | As an admin user, I want to create desks for branches so that merchants could serve their customers via multiple desks in branches | Merchant management | 345
384 | As an admin user, I want to create new users for merchants, so that can user the product | Merchant management | 345
385 | As an admin user, I want to have the list of Merchants so that I can manage them | Merchant management | 345
386 | As an admin user, I want to have the list of Merchants' desks so that I can manage them | Merchant management | 345
387 | As an admin user, I want to have the list of Merchants' users so that I can manage them | Merchant management | 345
388 | As an admin user, I want to have block/unblock, activate/deactivate functions for merchants, so that I can manage them. | Merchant management | 345
389 | As an admin user, I want to have block/unblock, activate/deactivate functions for merchants' desks, so that I can manage them | Merchant management | 345
390 | As an admin user, I want to have block/unblock, activate/deactivate functions for merchants' users, so that I can manage them | Merchant management | 345
391 | As an admin user, I want to have the list of orders so that I can view them | Applications Management | 347
392 | As an admin user, I want to have several search options in the list of orders so that I can search them easily | Applications Management | 347
393 | As an admin user, I want to have refund functionality, so that I can refund the orders | Applications Management | 347
394 | As an admin user, I want to export all the list that will be available in admin panel | Admin Panel | 327
395 | As an admin user I want to create other admin users so that my colleagues could use the admin portal | User Management | 343
396 | As an admin user, I want to have the list of admin users, so that I can view them | User Management | 343
397 | As an admin user, I wan to have search option with several filters in admin users' list so that I can search them easily | User Management | 343
398 | As a super admin user I want to have role management so that I can manage other admin users | User Management | 343
399 | As an admin user, I want to have reset password functionality, so that I can send new temp passwords to other admin users | User Management | 343
400 | As an admin user I want to have users' role management so that I can set roles for merchants' users | Merchant management | 345
401 | As an admin user I want to block/unblock, activate/deactivate merchants' users so that I can manage them | Merchant management | 345
403 | As an admin user, I want to assign merchants' users to branches and to desks, so that they can start using the product | Merchant management | 345
406 | As an admin user, I want to have search option with filtering in the merchants' users' list, so that I can find them easily | Merchant management | 345
412 | As a merchant, I want to have Profile section so that I can provide/edit information about my company | Admin Panel | 336
413 | As a merchant, I want to have security section so that I can change my password | Admin Panel | 336
414 | As a merchant, I want to have logout button, so that I can log out from the system | Admin Panel | 336
415 | As a user, when logging in via a temporary password, I want to set a new pass |  | 338
416 | As a user, when providing my username and password correctly I want to be logged in, so that I can use the system |  | 338
417 | As a user, I want to have Forgot Password functionality so that I can recover my password in case I will forget it |  | 338
418 | As a user, when providing wrong pass more then 3 times I want my user to be blocked, to prevent frauds |  | 338
419 | As a user, I want to have payments section, so that I can view my view my attached cards |  | 340
420 | As a user, I want to have add card functionality so that I can add another card for repayments |  | 340
421 | As a user, I want to have remove card function so that I can remove the cards that are not useful |  | 340
422 | As a user, I want to receive invitation link for new application so that I can start the financing flow |  | 341
423 | As a user, I want to receive a temp pass for the system so that I can login for the first time |  | 341
425 | As a user I want to have Terms and Conditions in new application final page, so that I can review it |  | 341
426 | As a user, I want to receive agreements when successfully passing the new financing flow, so that I can have them |  | 341
427 | As a user., I want to have my profile section, so that I can view/edit information about me |  | 342
428 | As a user, I want to have change password functionality in more section, so that I can change my pass |  | 342
429 | As a user I want to have support section so that I can contact support team to help me with issues |  | 342
430 | As a user, I want to have logout button so that I can log out from the system |  | 342

## Admin -UI
Task | % | Optimistic | Best guess | Pessimistic | Standard Deviation | Triangular Distribution | Three-point estimation | Delivery Range
Story 1 |  | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2 | 2.6667
Story 2 |  | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2 | 2.6667
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
|  | 2 | 4 | 6 |  | 4 | 4.6667 | 4 | 5.3333
|  | 2 | 4 | 6 |  | 4 | 4.6667 | 4 | 5.3333
|  | 2 | 4 | 6 |  | 4 | 4.6667 | 4 | 5.3333

## Devops-infra
Task | % | Optimistic | Best guess | Pessimistic | Standard Deviation | Triangular Distribution | Three-point estimation | Delivery Range
Move LeafLogix API to staging |  | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2 | 2.6667
Move LeafLogix API to production |  | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2 | 2.6667
Message Broker High Availabilty setup
Distributed Cache High Availability setup
RDS replication and monitorig setup
K8 Development enviroment |  |  |  |  | 0 | 0 | 0 | 0 | 0
K8 Stage enviroment |  |  |  |  | 0 | 0 | 0 | 0 | 0
K8 Production enviroment |  |  |  |  | 0 | 0 | 0 | 0 | 0
Monitoring and Metrics Setup |  |  |  |  | 0 | 0 | 0 | 0 | 0
Centralize logging setup
Vault Centralization
Core estimation |  | 2 | 4 | 6 |  | 4 | 4.6667 | 4 | 5.3333
Load persentage (for Agile) % | 20 | 2.4 | 4.8 | 7.2 |  | 4.8 | 5.6 | 4.8 | 6.4
Management Risk % | 20 | 2.88 | 5.76 | 8.64 |  | 5.76 | 6.72 | 5.76 | 7.68
Total